## SOV Sample
FREE SAMPLE — Schedule of Values (EXAMPLE)
EXAMPLE — sample data. Replace with your own.
Project ID | Description | Contract Value | % Complete | Earned to Date | Stored Materials | Retainage % | Retainage Withheld | Total Earned + Stored
P-001 | Mobilization & general conditions | 18500 | 100% |  | 0 | 10%
P-001 | Conduit & rough-in | 52000 | 80% |  | 0 | 10%
P-001 | Wire, devices & fixtures | 68400 | 45% |  | 8400 | 10%

## Pay App Sample
FREE SAMPLE — Pay Applications (EXAMPLE)
EXAMPLE — sample data. Replace with your own.
App # | Project ID | Period End | Gross Earned This Period | Stored Materials This Period | Retainage % | Retainage Withheld | Amount Due This Period | Status
1 | P-001 | 2026-08-31 | 60100 | 0 | 10% |  |  | Paid
2 | P-001 | 2026-09-30 | 49440 | 20900 | 10% |  |  | Submitted

## Lien Deadlines Sample
FREE SAMPLE — Lien Deadlines (EXAMPLE)
EXAMPLE — sample data. Deadlines are USER-ENTERED. This kit is NOT legal advice.
Project ID | Deadline Type | Deadline Date (USER-ENTERED) | Days Remaining | Alert | Status
P-001 | Lien deadline — Riverside Office Fit-Out (EXAMPLE) | 2027-03-15
P-001 | Preliminary notice follow-up — Riverside (EXAMPLE) | 2026-10-30
Formulas:
Days Remaining = IF([Deadline Date (USER-ENTERED)]="","",IFERROR([Deadline Date (USER-ENTERED)]-TODAY(),""))